## 22nd June deployment scope
S.No. | Jira ID | Summary | Issue raised by | Tester Name
1 | Rajesh A | RCU Remarks flowing from IRIS is not visible to RCU users in SFDC | RCU | Manju
2 | MDCJ-1871 | Approval Filename is not proper. It should be name of the approval: Need approval same name shown to the BO in SF | Operations | Pawan
3 | MDCJ-1650 | The snippets are not available in Ops screen for any of the checkpoints. If the snippets are not available i.e. not received from mobility, the snippet column should either be blank or NA should be displayed. As of now for everything "not found" is shown | Operations | Manju
4 | MDCJ-1855 | Documents & Snippets are not opening/loading with a single click. Have to click multiple times. | Operations | Sonia
5 | MDCJ-2033 | The document name shown on SF screen should be as per the selection made on mobility & not as per checkpoint excel | Operations | Sonia
6 | MDCJ-2037 | Ops checkpoints: (refer excel mailed) > Club “Authenticity Check” & “Validity” > “Validity” checkpoint to be mapped for CST/VAT > Utility bill>> supporting document checkpoint to be removed > Professional Tax certificate: Document ID to be added in checkpoints | Operations | Rohit
7 |  | Add button on home screen to direct super admin to Dashboard and reports as given to manage SLA | Operations | Sudipta

## 15th June deployment scope
Defect/CR# | Type | Description | Remark | Manual Test Designer | Reviewer
MDCJ-1864 | Mobility | Declaration & Review --> if GST number is provided as only Entity ID proof, then in Declaration & review section the GST state and address are not auto fetched |  | Pawan
MDCJ-1862 | Mobility | BO Rework --> if any case is reassigned to BO from branch or Ops or RCU, no intimation is provided by BO. BO needs to manually keeps checking |  | Rohit
MDCJ-1860 | Mobility | BO Rework - No message is shown once all the details are filled and user clicks on submit button. After sometime system navigates the user to dashboard |  | Rohit
MDCJ-1858 | Mobility | Bank Statement --> if bank name is selected first and then the user wants to change the bank statement, there is no option to search the bank name. User need to scroll and find the bank name |  | Pawan
MDCJ-1724 | Mobility | Entity Address Proof - If Rent agreement is selected as Entity Address Proof, then by default Utility bill becomes mandatory - CR |  | Ayaan
NA | Mobility | Turnover details text change (1 lakh instead of 100000) |  | Ayaan
NA | Mobility | Submit & Accept Ui Ux change - Colour of submit button not in standard red fill with white font |  | Ayaan
MDCJ-1704 | Mobility | _As per the checkpoint logic shared, 'Entity Details >>Entity Address' sub-checkpoint should be visible in all cases (i.e. if both Business address & communication address are same). |  | Mayur
New | Mobility | In case of Perfios success, checkpoints are still coming to ops |  | Mayur
New | Mobility | SVS upload API size restriction: Prop photo & Sign to be less than 5MB, otherwise the API is not called & the case is stuck with APPROVED status |  | Mayur
MDCJ-1650 | Operation | The snippets are not available in Ops screen for any of the checkpoints. If the snippets are not available i.e. not received from mobility, the snippet column should either be blank or NA should be displayed. As of now for everything "not found" is shown |  | Sudipta
MDCJ-1790 | Mobility | For Bank statement document: in case of nil IP, cancelled check to be uploaded alongwith bank statement, but the checkpoints are not reflecting for "Bank account statement // Cancelled cheque" on Ops
MDCJ-1871 | Mobility | Approval Filename is not proper. It should be name of the approval | Amit manwani to discuss with Jaspreet | Mayur
CR | RCU | Case details (Complete details of applicant/co applicant & SVR) to be made available in the same user id's of RCU users instead of multiple user id's |  | Manju N
CR | RCU | New queue to be created for RCU HOLD cases |  | Manju N
CR | RCU | RCU user should get option as "NA" at document level along with CLEAR/HOLD/SAMPLED |  | Manju N
CR | RCU | Complete details of SVR to me made available to RCU user's same as BO Users (PDF of SVR) |  | Manju N
CR | RCU | RCU Remarks flowing from IRIS is not visible to RCU users in SFDC |  | Sonia
CR | RCU | RCU remarks flowing from IRIS for CREDIT REFER/SUSPECT cases should be visible to BO users |  | Sonia
CR | RCU | If all documents are clear then RCU Decision should reflect as "SCREENED" in the history |  | Sonia
Defect | RCU | In case of IRIS decision is POSITIVE same is not visible in the history, same should reflect in history similar to CREDIT REFER/SUSPECT decisions along with remarks flowing from IRIS |  | Sonia
MDCJ-1821 | Operation | {CBS} Mobilt no. Country code not appearing on entity, AUS & Account level*-Â To be made compulsory on mobility to pass data with country code. Prasenjit to coordinate with mobility team. [Prasenjit] |  | Sonia
MDCJ-1855 | Operation | Documents & Snippets are not opening/loading with a single click. Have to click multiple times. |  | Ayaan
MDCJ-1961 | Mobility +Operation | OMNIDOCS: Refer details in attached mail |  | Pawan
NA | CBS | {CBS} SMS Flag not getting updated at entity & AUS UCIC anywhere |  | Mayur
NA | CBS | {CBS} statement frequency at account level not updated |  | Mayur
NA | CBS | {CBS} Mobile no. & Email ID at account level not updated |  | Mayur
NA | CBS | {CBS} Mandate Matrix API |  | Mayur
NA | CBS | {CBS} Upload signatory |  | Mayur
NA | CBS | {CBS} Internet Banking |  | Mayur
NA | CKYC | {CKYC} Citizenship Value, Product segment, Country of incorporation, KYC attestation type |  | Mayur
MDCJ-1652 | Operation | _This issue was raised in UAT-1 excel._ The cases are still not visible in User's queue unless the web-page is refreshed. Moving between various queues should refresh the case list, but same is not happening. No button is available for refresh on SF screen. |  | Manju N
MDCJ-1712 | Operation | Unable to view the uploaded excel/mail attachment in CRILC. It was mentioned by PSL team that excel attachment will open in its own app. Hence the download button should be available so that the user can view the crilc uploaded |  | Sudipta
MDCJ-1716 | Operation | At the top label â€œETB ¦ UCIC â€“ Entityâ€ & â€œETB ¦ UCIC - AUS_1â€ is NO but system is still showing the UCIC no. (it should be blank). Pls check the mapping SF and Mobility Team need to internally discuss on this (the ETB/NTB check shows NO but the value is shown as YES in SF) |  | Sudipta/Manju
NA | Operation | Reports should not to be editable to any user or atleast on refresh changes should be removed. Any change should not impat the report for other users. |  | Sudipta
NA | Mobility +Operation | GST Annexure address not being shown on SF screen |  | Ayaan
NA | Mobility +Operation | GST Annexure ID not being shown onSF screen |  | Ayaan

## Phase 2 design tracker
Sr.No # | Scope Type | Feature | User Story Status | VD Status | Remark | Manual Test Designer | Reviewer | Manual Test Design Completion | #Total Test Cases | #Regression Test Cases | #Automation Tester | #Test Cases Automated | Automation Completion Status | Remark
1 | Enhanment acoss jouney | Aadhaar biometric | Signed Off | Signed Off |  | Pawan | Pawan/Ashish
2 |  | Choice account | Signed Off | Signed Off |  | Pawan/Ashish | Pawan/Ashish
3 |  | Auto approvals | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
4 |  | Digital initial funding | Pending Req | Pending Req |  | Mayur | Pawan/Ashish
5 |  | Cross sell - SA integrated | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
6 |  | Cross sell - BBG questionairre based lead sharing | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
7 |  | Cross sell - OD First integrated | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
8 |  | Cross sell - PL integrated | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
9 |  | Cross sell - CC integrated | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
10 |  | Cross sell - POS machine | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
11 |  | Cross sell -beyond banking | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
12 |  | Cross sell -Home loan, auto loan, insurance (lead share) | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
13 |  | Branch team login - dashboard & assign/re-assign cases |  |  | CRM SFDC | Sudipta | Pawan/Ashish
14 |  | Branch team reports |  |  | CRM SFDC | Sudipta | Pawan/Ashish
15 |  | QC team digital flow | Pending Req |  |  | Sudipta | Pawan/Ashish
16 |  | Addl. Karzaa integrations (IEC, Shop & establishment, professional bodies) | Pending Req |  |  | Pawan | Pawan/Ashish
17 |  | Addl. Simplifi integrations (IEC, Shop & establishment, other doc) | Signed Off | Error handling -VD Completed | Shop @establishment not coved | Rohit | Pawan/Ashish
18 |  | OCR based extracted text match for STP |  |  |  | Rohit | Pawan/Ashish
19 |  | OCR extracted text math % |  |  |  | Rohit | Pawan/Ashish
20 |  | STP flow for ops, RCU |  |  | SF | Mayur | Pawan/Ashish
21 |  | E-SVR, SVR via vendor | Pending Req | Pending Req |  | Mayur | Pawan/Ashish
22 |  | Addl digilocker docs - passport, DL, voter ID | Pending Req | Pending Req |  | Pawan | Pawan/Ashish
23 |  | STP flow for ops, RCU |  |  | SF | Mayur | Pawan/Ashish
24 |  | Bulk upload for CRIL-C, priority flagging |  |  | SF | Pawan | Pawan/Ashish
25 | Phase 2 req | Enter basic details, business details | Sent for review | Sent for review |  | Ayaan | Pawan/Ashish
26 |  | Enter AUS details, auto-fetch Beneficiary owner details via Karzaa | Sent for review | Sent for review |  | Pawan | Pawan/Ashish
27 |  | Auto-fetch company docs :- AOA, MOA, COI, list of directors, list of shareholders from MCA via Signzy/Karza | NA | NA | Use story revised | Pawan | Pawan/Ashish
28 |  | self KYC link with v-KYC in case of multiple AUS, BO's | Draft sent for review | In Progess | req completion pending | Sudipta | Pawan/Ashish
29 |  | Board resolution 1) Digitally generated via in-app template, digital signatures 2) OCR for physical BR uploaded in IDFC First format 3) Physical BR uploaded in company customized format | Pending Req | Pending Req |  | Sudipta | Pawan/Ashish
30 |  | MCA integration for new corporates | Draft sent for review | Pending Req | req completion pending | Ayaan | Pawan/Ashish
31 |  | FATCA declarations, other mandatory declarations | Pending Req | Pending Req |  | Ayaan | Pawan/Ashish
32 |  | Journey design w. changes to Pvt Ltd journey for partnership & other constitutions | Pending Req | Pending Req |  | Mayur | Pawan/Ashish
33 |  | Shorter Route for Converting MCA leads | Pending Req | Pending Req |  | Mayur | Pawan/Ashish
34 | Phase 1 deferred featues | BO Rework full edit |  |  | SF | Rohit/Ashish | Pawan/Ashish
35 |  | Async implementaion |  |  |  | Mayur/Ashish | Pawan/Ashish

## Phase 2 feature-breakdown
Sr.No # | Scope Type | Feature | User Story Status | VD Status | Remark | Manual Test Designer | Reviewer | Manual Test Design Completion | #Total Test Cases | #Regression Test Cases | #Automation Tester | #Test Cases Automated | Automation Completion Status | Remark
|  | Customer Details | Signed Off | Under IDFC Review |  | Sudipta | Pawan
|  | Add Business and Authorised Signatories Details: Basic Details | Awaiting inputs from IDFC | Under IDFC Review |  | Sudipta | Pawan
|  | Add Business and Authorised Signatories Details:GST Details | Under IDFC Review | Under IDFC Review |  | Sudipta | Pawan
|  | Add Business and Authorised Signatories Details:Address and Contact Details | Signed Off | Under IDFC Review |  | Sudipta | Pawan
|  | Add Business and Authorised Signatories Details:Director Details | Pending internal compliance discussion | Under IDFC Review |  | Ayaan | Pawan
|  | Select KYC Method | Signed Off | Under IDFC Review |  | Ayaan | Pawan
|  | In Person KYC | Signed Off | Under IDFC Review |  | Ayaan | Pawan
|  | Video KYC |  | In Progress |  | Ayaan | Pawan
|  | Product Selection |  | TBD |  | Mayur | Pawan
|  | Mandatory Company Documents | Signed Off | Under IDFC Review |  | Mayur | Pawan
|  | Converting lead from MCA website | Awaiting inputs from IDFC | TBD |  | Pawan | Pawan
|  | Simplyfi Validator - DL, IEC, Cheque, MITC | Signed Off |  |  | Mayur | Pawan
|  | Simplyfi Snippet - DL, IEC, Cheque, MITC | Signed Off |  |  | Mayur | Pawan
|  | Extracted Snippet Text Match Percentage |  |  |  | Mayur | Pawan
|  | Shorter solution for converting MCA lead |  |  |  | Pawan | Pawan
|  | Credit Bureau |  |  |  | Pawan | Pawan
|  | ETB NTB Check |  |  |  | Mayur | Pawan

## Questionarie
Sr. No | Feature Name | Feature Description | Req Understanding | Questionarie | Assigned to
1 | Choice Account No | Allowing user to select Account no of their choice |  | When BO selected Use of Mobile number or Use of Date of Birth- input boxes will be displayed to BO or directly 10 options will be displayed
2 | Choice Account No | Allowing user to select Account no of their choice |  | When BO selects option - I want to choose my own account number- and select End with and enter 10 digits- VD doesnt show 1st digit as X or dropdown
3 | Choice Account No | Allowing user to select Account no of their choice |  | Is 45 Days value configurable for reserving account number?